## Full experiments
FinPersona-Bench: full experiment plan
Grouped by stage, in order. Each group depends on the groups above it. Any change to the environment or prompts after group 0 restarts from group 0.
# | Task | Details | Check / output | Needs | Assigned to | Status
0 Environment freeze
0.1 | Apply remaining generator fixes | Randomised price scale per seed; analyst error sd; jump-rate reconciliation; blow-off multiplier; IV forecast timing. | Fixes listed in the decision log with before / after numbers. |  |  | To do
0.2 | Re-run stylized-facts checklist | 50 seeds per scenario, crash per severity, T = 200; plus the long-horizon phase-free control. | Checklist table: passes and accepted fails with reasons. | 0.1 |  | To do
0.3 | Re-run leakage audit L1, L2, L2b, L4 | Held-out seeds; price-only and shuffled-value controls. | L2 calm R2 at or below threshold; L1 no inversion; L2b selectivity within margin; L4 coverage table. | 0.1 |  | To do
0.4 | Re-run hazard calibration | Bubble top grid (h0, b, g_max). | Topped share 40 to 60 percent; peak P/V in range. | 0.1 |  | To do
0.5 | Run L3 LLM probe | A few frontier models asked to estimate value and sign from the rendered observation; stratified by scenario, phase, seed. | Sign accuracy minus shuffled baseline within the surrogate bound; MAPE within bound; Wilson CIs. | 0.3 |  | To do
0.6 | Generator sensitivities | Engine variants (index parameters, half-life brackets), panic multiplier, omega scaling. | Sensitivity table beside the main checklist. | 0.2 |  | To do
0.7 | Freeze generator | Record config hash and code hash; update the generator spec; tag the freeze. | Hashes stable; spec matches code. | 0.2 to 0.6 |  | To do
0.8 | Reproducibility check | Same seed gives the same path across threads and runs. | Zero mismatching paths. | 0.7 |  | To do
1 Harness smoke test
1.1 | Rendered prompt check | Compare the rendered static and memory prompts and every arm against the published samples. | Byte-identical; prompt hash recorded. | 0.7 |  | To do
1.2 | All arms once on a cheap model | Static, memory, declarative placebo, directive placebo, wrapper-only, swapped, no-mandate trader; a few seeds; each scenario. | 100 percent parsed; all rows present. | 1.1 |  | To do
1.3 | Restatement probe | Forked probe on schedule in the memory arm. | Probe answers logged; not in the transcript. | 1.2 |  | To do
1.4 | One stateful run | Rolling context, mandate in the system prompt. | Token count grows per step; mandate offset logged. | 1.2 |  | To do
1.5 | Provenance | Env version, config hash, prompt hash, temperature, git commit in every row. | No empty provenance cells. | 1.2 |  | To do
1.6 | Report and stats pipelines | Run the report and the statistics scripts on the smoke output. | Tables produced without errors. | 1.2 to 1.5 |  | To do
2 M0: open-weight coverage and t = 0 gate
2.1 | Fix the open-weight roster | At least 3 families; include one larger model (32B to 70B). | Roster and licences documented. | 1.6 |  | To do
2.2 | Static and memory arms on the roster | All personas, scenarios, seeds; start at band centre. | Runs complete; reliability table. | 2.1 |  | To do
2.3 | Common-start slice | Static arm, start 0.5, all scenarios. | Runs complete. | 2.1 |  | To do
2.4 | Behavioural metrics per model | Band-MAS, mandate-conditional regret, drawdown, net return. | Per-model table. | 2.2 |  | To do
2.5 | t = 0 separability gate | Day-1 ordering, band hit, decodability, surrogate share; per model and family. | Pass / fail per model recorded. | 2.3 |  | To do
2.6 | Choose anchor models for mech-interp | From gate passers, covering at least 3 families and sizes. | Anchor list and reasons written down. | 2.5 |  | To do
2.7 | Zero-trade and fallback shares | Per model and arm. | Table. | 2.2 |  | To do
3 Main behavioural grid
3.1 | Core arms: static and memory | All models x 3 personas x all scenarios (crash per severity) x seeds x decode replicates; start at band centre; Track B. | Runs complete; reliability table. | 1.6 |  | To do
3.2 | Placebo arms | Declarative placebo, directive placebo, wrapper-only; same grid. | Runs complete. | 3.1 |  | To do
3.3 | Swapped mandate and no-mandate trader | Same grid; trader starts at 0.5. | Runs complete. | 3.1 |  | To do
3.4 | Track A slice | Band stated in the prompt; subset of models and scenarios. | Runs complete. | 3.1 |  | To do
3.5 | O3 numerical-only arm | Target stated, persona text removed. | Runs complete. | 3.1 |  | To do
3.6 | Common-start slice | All personas start at 0.5; static and memory. | Runs complete. | 3.1 |  | To do
3.7 | Mandate wording variants | Paraphrased and abbreviated mandates; subset. | Runs complete. | 3.1 |  | To do
3.8 | Baselines and oracles per cell | Trivial policies, constant mix, momentum, mean reversion, value oracle, mandate-conditional oracle, observables oracle; same start as the cell. | Envelope per cell; degenerate normalisations flagged. | 3.1 |  | To do
3.9 | Reliability and degeneracy audit | Parse, fallback, zero-trade shares; degenerate normalisation flags. | Audit table clean. | 3.1 to 3.7 |  | To do
3.10 | Spot-check runs against logs | A handful of runs replayed end to end. | No mismatches. | 3.9 |  | To do
4 Causal decomposition analysis (no new runs)
4.1 | Per-arm contrasts vs static | Every arm, every metric, model level. | Contrast table with CIs. | 3.9 |  | To do
4.2 | Content test | Swapped mandate moves allocation to the injected side? | Model-level sign counts and effect sizes. | 4.1 |  | To do
4.3 | Force test | Directive placebo and wrapper-only vs mandate. | Model-level sign counts and effect sizes. | 4.1 |  | To do
4.4 | Sign reversal by persona x regime | Memory effect by persona and scenario; topped / not topped; crash severity. | Per-family conclusion. | 4.1 |  | To do
4.5 | Statistics | Mixed effects with random slopes by model; BH across the metric family; effect sizes with CIs. | Statistics tables. | 4.1 to 4.4 |  | To do
5 Persona and salience analysis
5.1 | Salience surrogate | Per model per window; persona share vs directive share; label-permutation null; O3 ceiling. | Null near zero; O3 high; blocked CV by seed. | 3.9 |  | To do
5.2 | OCEAN grid | Trait-space sampling on the full roster. | Runs complete; analysed as 5.1. | 3.1 |  | To do
5.3 | Track A vs Track B | Stated band vs persona text only. | Comparison table with CIs. | 3.4 |  | To do
5.4 | Persona-share report | Persona share and directive share per model and family. | Report with CIs. | 5.1 to 5.3 |  | To do
6 Stateful grid (decay test)
6.1 | Stateful runs | Anchor models x scenarios x seeds; rolling context; mandate in the system prompt. | Runs complete; token counts logged per step. | 2.6 |  | To do
6.2 | Restatement probe | On schedule; answers logged. | Probe accuracy per window. | 6.1 |  | To do
6.3 | Windowed adherence statistics | Against a constant-exposure null; phase controlled. | Decay test result per model. | 6.1 |  | To do
6.4 | Long-horizon control | One model, extended horizon. | Runs complete; same analysis. | 6.1 |  | To do
7 Mechanistic: M1 and M2 (details on sheet 2)
7.1 | Replay infrastructure | Replay on the new renderer; span maps regenerated; hash verification. | Replayed prompts reproduce the logged hashes. | 3.9, 6.1 |  | To do
7.2 | Numeric read-out check | Action read-out for the target cash share; query position fixed. | Matches real generation on a sample. | 7.1 |  | To do
7.3 | M1 attention, grid replay | Per arm, per phase; placebo, uniform and sink controls; per layer at the decision position. | Attention tables and series with CIs. | 7.2 |  | To do
7.4 | M1 recency placebo | Neutral length-matched block at the re-injection position. | Position vs content effect separated. | 7.3 |  | To do
7.5 | M1 stateful replay | Full 200-day context of the stateful agent; probe turns excluded. | Front-mandate attention over the real rollout. | 7.2, 6.1 |  | To do
7.6 | M2 mandate-presence direction | Contrastive prompts and swapped-mandate pairs; projection static vs memory explained. | Direction and projection plots. | 7.2 |  | To do
7.7 | M2 adherence direction | Next-action label; common-start slice; held-out scenario and persona; drift on the stateful arm. | Held-out AUROC with confound check. | 7.6 |  | To do
7.8 | Characterise the direction | Cosines vs aggressive-conservative, trade-hold and persona-specific directions. | Table. | 7.6 |  | To do
8 Mechanistic: M3, then M4 (details on sheet 2)
8.1 | Steering operating range | Valid alpha range per model from output validity. | Range recorded per model. | 7.6 |  | To do
8.2 | Dose-response and ablate-restore | 3 or more seeds; all personas; all scenarios incl. sustained bull; scored with band-MAS, mandate-conditional regret, drawdown; allocation plotted. | Monotone inside range; ablate worsens, restore recovers; sustained bull: adherence moves, regret does not. | 8.1 |  | To do
8.3 | Random and orthogonal controls | Same alpha; behaviour and output validity. | Controls table. | 8.1 |  | To do
8.4 | Mediation test | Ablate the direction inside the memory arm; static plus direction vs memory. | Memory benefit with and without the direction. | 8.2 |  | To do
8.5 | Layer sweep | Steering layer swept; effect per layer. | Table. | 8.2 |  | To do
8.6 | M4 gate re-check | Crash reversal under band-centre start and target-share action, per model. | Gate table; go / no-go for 8.7. | 3.9 |  | To do
8.7 | M4 attribution | Only if 8.6 passes: numeric logit read-out; path or activation patching of the mandate span; many crash days. | Attribution result or documented no-go. | 8.6 |  | To do
9 Controller and frequency sweep
9.1 | Injection-frequency sweep | On the behavioural metric, with token cost. | Sweep curve with cost axis. | 3.9 |  | To do
9.2 | Adaptive controller | Re-inject when the M2 projection crosses a threshold; implemented in the harness. | Controller runs on anchor models. | 7.7 |  | To do
9.3 | Controller comparison | Vs always-on, the sweep and a score-based trigger; per regime; token cost. | Comparison table per regime. | 9.1, 9.2 |  | To do
10 Sensitivities (subset of the grid)
10.1 | Cost tier and visibility | 0 / 5 / 20 bp; hidden vs shown. | Headline contrasts with and without. | 3.9 |  | To do
10.2 | Execution timing | Same-day close vs next open. | Same. | 3.9 |  | To do
10.3 | Start design | Band centre vs common 0.5 vs 100 percent cash. | Same. | 3.9 |  | To do
10.4 | Action interface | Target share vs the fraction interface. | Same. | 3.9 |  | To do
10.5 | Field order | Canonical vs randomised per seed. | Same. | 3.9 |  | To do
10.6 | Horizon disclosure | Undisclosed vs disclosed. | Same. | 3.9 |  | To do
10.7 | Metric parameters | Resolvability threshold; band width; crash severity set. | Same. | 3.9 |  | To do
11 Final scoring, statistics and figures
11.1 | Re-score everything | Final metric definitions applied to all runs. | One scoring script; one results table. | all |  | To do
11.2 | Statistics tables | Mixed effects, BH, effect sizes, CIs. | Tables ready for the paper. | 11.1 |  | To do
11.3 | Audit and checklist tables | Leakage audit, checklist, baseline envelope, gate table. | Tables ready for the paper. | 0.2 to 0.5 |  | To do
11.4 | Figures | All figures regenerated from code. | Figure scripts checked in. | 11.1 |  | To do
11.5 | Results sections | Written from the tables only; every number traces to a run file and a script. | Trace list complete. | 11.2 to 11.4 |  | To do

## Mech-interp changes
Mechanistic interpretability: changes before re-running M1 to M4
Env alignment = needed to fit the new environment (all required). Design = controls, robustness and variability (by priority). Task = where it lands on sheet 1.
# | Type | Change | What to do | Why | Priority | Task | Assigned to | Status
A Environment alignment (all required)
1 | Env alignment | Prompt replay | Replay on the new renderer (19 fields + cash share). Verify by reproducing the logged prompt and config hashes. | All span offsets change; the hash proves the replay is the real prompt. | Required | 7.1 |  | To do
2 | Env alignment | Token spans | Regenerate all spans. Add spans for the new arms and the analyst fair-value field. | New arms are new text blocks. | Required | 7.1 |  | To do
3 | Env alignment | Action read-out | Read the numeric target cash share. Redo the read-out check. Fix the query position (first digit token). | The action is a number now, not BUY / SELL / HOLD. | Required | 7.2 |  | To do
4 | Env alignment | M4 logit target | Define a numeric read-out (high-cash vs low-cash tokens, or above / below current share) before any attribution. | The SELL and HOLD logits no longer exist. | Required | 8.7 |  | To do
5 | Env alignment | M4 gate | Re-check which models show the crash reversal under band-centre start and target-share action. | The old 'frozen cash' story depends on the old start and the SELL no-op. | Required | 8.6 |  | To do
6 | Env alignment | Adherence labels | Redefine on band deviation (centres 0.10 / 0.50 / 0.80). Re-choose cut-offs. Rebalance. | Targets changed. | Required | 7.7 |  | To do
7 | Env alignment | Behavioural scores | Re-score with band-MAS, mandate-conditional regret (resolvable steps), drawdown, net return. Normalise by floor and ceiling. | Old Rationality produced the sign-flip by construction. | Required | 8.2 |  | To do
8 | Env alignment | Time alignment | Align by generator phase labels. Report per phase. Stratify topped / not topped and by crash severity. | Phase onsets are randomised per seed. | Required | 7.3 |  | To do
9 | Env alignment | Scenarios | Add sustained bull to M3. | Adherence should move, regret should not. | Required | 8.2 |  | To do
10 | Env alignment | Start design | Main runs at band centre. Train directions on the common-start (0.5) slice. | Breaks the persona / portfolio-state correlation. | Required | 7.7 |  | To do
11 | Env alignment | Cash share in prompt | Treat the printed cash share as a known confound for any adherence direction. | The current adherence direction reads this number. | Required | 7.7 |  | To do
12 | Env alignment | Arms | Run M1 on every arm. Use swapped-mandate pairs as the M2 contrast. | Gives the content-vs-force test inside the model. | Required | 7.3, 7.6 |  | To do
13 | Env alignment | Stateful agent | Replay the real stateful agent's full 200-day context. Measure attention, projection and behaviour together. Exclude probe turns. | The only place decay can be tested. | Required | 7.5 |  | To do
14 | Env alignment | Decoding | Match the harness (temp 0.2, 3 or more decodes) or log greedy as a factor. | Comparability with the behavioural grid. | Required | 8.2 |  | To do
15 | Env alignment | Provenance | Stamp env version, config hash and prompt hash into every output row. Use the grid's seeds. | Same standard as the behavioural runs. | Required | 7.1 |  | To do
B Design: controls, robustness, variability
16 | Design | Mediation test | Ablate the mandate direction inside the memory arm. Does the memory benefit vanish? Does static + direction reproduce memory? | M3 shows the direction can move behaviour, not that re-injection works through it. | High | 8.4 |  | To do
17 | Design | Projection reversal | Refit the direction on both prompt forms, or on the swapped-mandate contrast. Re-plot static vs memory. | Static projects higher than memory now; contradicts the story. | High | 7.6 |  | To do
18 | Design | Recency placebo (M1) | Put a neutral, length-matched block at the re-injection position. Measure its attention and its effect on behaviour. | Separates position effect from content effect. | High | 7.4 |  | To do
19 | Design | Report allocation | Plot cash share vs alpha. Mark saturation at all-in / all-cash. | The MAS plateau hides that the agent went all-in. | High | 8.2 |  | To do
20 | Design | Characterise the direction | Compare with aggressive-vs-conservative, trade-vs-hold and persona-specific directions. Report cosines. | Are we steering 'persona' or just 'invest more'? | High | 7.8 |  | To do
21 | Design | Steering controls | Steer random and orthogonal directions at the same alpha. Report behaviour and output validity. | Any push that size might move behaviour. | High | 8.3 |  | To do
22 | Design | Adherence direction | Label by the next action's deviation, not the printed cash share. Train on the common-start slice. Test on held-out scenario and persona. Check drift on the stateful arm. | Needed before it can drive the controller. | High | 7.7 |  | To do
23 | Design | Seeds and CIs | 3 or more seeds per model and persona. CIs on every ratio and curve. | Gemma and Qwen are 1 seed, ENTJ only. | High | 8.2 |  | To do
24 | Design | Model roster | Anchors chosen by the t = 0 gate from M0. 3 or more families. Add one larger model (32B to 70B). | 3 anchors of 7 to 9B, chosen by convenience. | High | 2.1, 2.6 |  | To do
25 | Design | Sustained-bull test | Run M3 on sustained bull. | Adherence should move; regret should not. | High | 8.2 |  | To do
26 | Design | Layer sweep | Sweep the steering layer. Report effect per layer. | Mid-layer band was chosen by hand. | Medium | 8.5 |  | To do
27 | Design | Per-layer attention | Report per layer at the decision position. Normalise by 1 minus sink share. | Pooling hides layer structure; Llama puts half its attention on token 0. | Medium | 7.3 |  | To do
28 | Design | Value-weighted attention | Weight by value-vector norm, or use attention rollout, as a second measure. | Raw pattern shows where the model looks, not what it reads. | Medium | 7.3 |  | To do
29 | Design | Stronger M4 | Path or activation patching of the mandate span into the static run. Many more crash days. | Layer-wise attribution differences do not establish a path. | Medium | 8.7 |  | To do
30 | Design | Persona coverage | Full M3 grid for ISFJ and INTJ. Persona-specific directions. | Headline generalises from ENTJ. | Medium | 8.2 |  | To do
31 | Design | Wording variants | Repeat M1 and M2 with paraphrased and abbreviated mandates. | Shows dependence on exact wording. | Medium | 7.3, 7.6 |  | To do
32 | Design | Operating range | Set the valid alpha range per model from output validity. Report only inside it. | Alpha 0.2 and below minus 0.1 break the model. | Medium | 8.1 |  | To do
33 | Design | Restore-at-layer | More days and seeds. Report intervals. | Current curve is one spike on 20 days. | Low | 8.5 |  | To do
34 | Design | Attention to market | Report the drop in market-block attention under memory, per regime. | Candidate mechanism for the bubble penalty. | Low | 7.3 |  | To do